## SCOPE_BUDGET
Wellfleet_Herring_River_ FY22 MVP Action Grant Scope/Budget
Instructions: -Fill out this table completely for each task and sub-task proposed. Add or delete lines as necessary and incorporate into existing formulas. -Round to nearest whole number. -Remember to include the proposed items from your public involvement and community engagement plan (Question 5 in the Application). -Keep in mind that MVP reimburses as tasks or sub-tasks are completed and identified deliverables are received, so if it is important to your community to be reimbursed throughout the grant period, please split up tasks accordingly and include interim deliverables as necessary. - For all major project deliverables make sure you have a line for both the draft and final deliverable with at least two weeks in between. Regional Coordinators must review all major draft deliverables prior to finalization. -The second tab on this spreadsheet is optional but can be used to: 1) calculate budget numbers to the extent helpful; 2) identify assumed rates for project team time and municipal in-kind match; or 3) justify high grant funding requests for specific tasks by providing greater detail. You may also use another format to provide greater detail on these items (e.g., a quote from a vendor or a differently formatted spreadsheet).
Project Task Description | Deliverables | Approximate Start Date | Approximate End Date | Total Grant [No municipal staff time] | In-Kind Match | Cash Match | Total Match | Total
Tasks to be Completed by June 30, 2022
Required Task 0: Project kickoff
Sub-task 0.1: Kick-off meeting with Town, EEA, and Consultant | Meeting notes, sign-in sheet | September 7, 2021 | September 7, 2021 | 0 | 491 |  | 491 | 491
Total Task 0 Cost |  |  |  | 0 | 491 | 0 | 491 | 491
Task 1: Chequessett Neck Road Bridge and Water Access Facility Construction Plans and Bid Specifications
Sub-task 1.1 Review/Update 60% Design Documents | included in SubTask 2.3 and 2.4 deliverables | October 12, 2021 | October 29, 2021 | 10000 |  |  | 0 | 10000
Sub-task 1.2 Develop Traffic Management Plan | Draft and Final TMP | January 15, 2022 | June 30, 2022 | 10000 |  |  | 0 | 10000
Sub-task 1.3 Prepare Draft Final Design Plans | Draft and Final plans including responses to comments | November 1, 2021 | December 3, 2021 | 150000 |  |  | 0 | 150000
Sub-task 1.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | Draft and Final Construction Plans, Specifications and Esitimates | December 3, 2021 | June 30, 2022 | 85000 | 5527 | 20000 | 25527 | 110527
Sub-task 1.5 MassDOT PS&E Final Review and Coordination | Completed Project Scoping Checklist and Access Permit | April 4, 2022 | June 30, 2022 | 0 | 3017 | 70000 | 73017 | 73017
Sub-task 1.6 Town and DOT Review/Coordination Meetings | Meeting notes including participants and action items | September 13, 2021 | June 30, 2022 | 8000 | 2978 | 7000 | 9978 | 17978
Total Task 1 Cost |  |  |  | 263000 | 11522 | 97000 | 108522 | 371522
Task 2: High Toss Road Construction Plans and Bid Specifications
Sub-task 2.1 Review/Update 60% Design Documents | included in SubTask 2.3 and 2.4 deliverables | October 12, 2021 | October 29, 2021 | 425 | 69 | 10000 | 10069 | 10494
Sub-task 2.2 Develop Traffic Management Plan | Draft and Final TMP | October 12, 2021 | June 30, 2022 | 4345 | 685 | 2000 | 2685 | 7030
Sub-task 2.3 Prepare Draft Final Design Plans | Draft and Final plans including responses to comments | November 1, 2021 | December 3, 2021 | 31505 | 181 | 3000 | 3181 | 34686
Sub-task 2.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | Draft and Final Construction Plans, Specifications and Esitimates | December 3, 2021 | June 30, 2022 | 17560 | 648 |  | 648 | 18208
Sub-task 2.5 Meetings and Project Communication | Meeting notes including participants and action items | September 13, 2021 | June 30, 2022 | 3420 | 1069 |  | 1069 | 4489
Total Task 2 Cost |  |  |  | 57255 | 2652 | 15000 | 17652 | 74907
Task 3: Low-Lying Roads Elevation and Culvert Replacements Construction Plans and Bid Specifications
Sub-task 3.1 Review/Update 60% Design Documents | included in SubTask 3.3 and 3.4 deliverables | October 12, 2021 | October 29, 2021 | 10630 | 138 | 10000 | 10138 | 20768
Sub-task 3.2 Develop Traffic Management Plan | Draft and Final TMP | October 12, 2021 | June 30, 2022 | 12650 | 1061 | 5000 | 6061 | 18711
Sub-task 3.3 Prepare Draft Final Design Plans | Draft and Final plans including responses to comments | November 1, 2021 | December 3, 2021 | 76720 | 523 | 5000 | 5523 | 82243
Sub-task 3.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | Draft and Final Construction Plans, Specifications and Esitimates | December 3, 2021 | June 30, 2022 | 38310 | 710 |  | 710 | 39020
Sub-task 3.5 Meetings and Project Communication | Meeting notes including participants and action items | September 13, 2021 | June 30, 2022 | 5670 | 992 |  | 992 | 6662
Total Task 3 Cost |  |  |  | 143980 | 3424 | 20000 | 23424 | 167404
Task 4: Low-Lying Property Mitigation, Way #672 (25 and 27 Way #672, inc utilities) Construction Plans and Bid Specifications
Sub-task 4.1 Review/Update 60% Design Documents | included in SubTask 4.3 and 4.4 deliverables | October 12, 2021 | October 29, 2021 | 2735 | 333 | 10000 | 10333 | 13068
Sub-task 4.2 Develop Traffic Management Plan | Draft and Final TMP | October 12, 2021 | June 30, 2022 | 5115 | 125 |  | 125 | 5240
Sub-task 4.3 Prepare Draft Final Design Plans | Draft plans including responses to comments | November 1, 2021 | December 3, 2021 | 40115 | 340 | 7000 | 7340 | 47455
Sub-task 4.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | Final Construction Plans, Specifications and Estimates | December 3, 2021 | June 30, 2022 | 27695 | 989 |  | 989 | 28684
Sub-task 4.5 Meetings and Project Communication | Meeting notes including participants and action items | September 13, 2021 | June 30, 2022 | 8190 | 1737 |  | 1737 | 9927
Total Task 4 Cost |  |  |  | 83850 | 3524 | 17000 | 20524 | 104374
Task 5: Low-Lying Property Mitigation, Miller-Frederiksen (695 Bound Brook Island Road) Construction Plans and Bid Specifications
Sub-task 5.1 Review/Update 60% Design Documents | included in SubTask 5.2 and 5.3 deliverables | October 12, 2021 | October 29, 2021 | 775 | 69 | 4000 | 4069 | 4844
Sub-task 5.2 Prepare Draft Final Design Plans | Draft and Final plans including responses to comments | November 1, 2021 | December 3, 2021 | 4695 | 69 | 3000 | 3069 | 7764
Sub-task 5.3 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | Draft and Final Construction Plans, Specifications and Esitimates | December 3, 2021 | June 30, 2022 | 4805 | 348 |  | 348 | 5153
Sub-task 5.4 Meetings and Project Communication | Meeting notes including participants and action items | September 13, 2021 | June 30, 2022 | 2600 | 743 |  | 743 | 3343
Total Task 5 Cost |  |  |  | 12875 | 1229 | 7000 | 8229 | 21104
Task 6: Chequessett Yacht and Country Club Reconfiguration Construction Plans and Bid Specifications
Sub-task 6.1 Review/Update 60% Deisign Documents | included in SubTask 6.2 and 6.3 deliverables | October 12, 2021 | October 29, 2021 | 4000 | 377 | 5000 | 5377 | 9377
Sub-task 6.2 Develop Traffic Management Plan | Draft and Final TMP | November 1, 2021 | December 3, 2021 | 2000
Sub-task 6.3 Prepare Draft Final Design Plans | Draft plans including responses to comments | December 3, 2021 | June 30, 2022 | 13000 | 146 | 5000 | 5146 | 18146
Sub-task 6.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | Final Construction Plans, Specifications and Esitimates | September 13, 2021 | June 30, 2022 | 8000 | 564 |  | 564 | 8564
Sub-task 6.5 Meetings and Communcation | Meeting notes including participants and action items | September 13, 2021 | June 30, 2022 | 2000 | 656 |  | 656 | 2656
Total Task 6 Cost |  |  |  | 29000 | 1743 | 10000 | 11743 | 38743
Task 7: Public Involvement and Community Engagement Plan
Development of Public Outreach Material | Mailings, Brochures, Posters, Flyersetc | October 12, 2021 | October 29, 2021 | 0 | 1467 | 5000 | 6467 | 6467
Public meetings (HREC, HRSG) | agendas, minutes, recordings of meetings | October 12, 2021 | June 30, 2022 | 0 | 1483 |  | 1483 | 1483
Special events, personal meetings | participant lists, meeting notes | May 31, 2022 | December 3, 2021 | 0 | 2242 | 0 | 2242 | 2242
|  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  | 0 | 0
Total Task 7 Cost |  |  |  | 0 | 5192 | 5000 | 10192 | 10192
Required Task 8: Reporting
Sub-task 8.1 Monthly progress reports FY22 (template provided) | Monthly progress reports submitted by the 30th of each month of the grant period to your MVP Regional Coordinator | October 30, 2021 | June 30, 2022 | 0 | 1654 |  | 1654 | 1654
Sub-task 8.2 Project Case Study (template provided) | Final case study report, powerpoint slide, project photos | May 31, 2022 | June 30, 2022 | 0 | 793 |  | 793 | 793
Total Task 8 Cost |  |  |  | 0 | 2447 | 0 | 2447 | 2447
TOTAL PROJECT COST FY22 |  |  |  | 589960 | 32224 | 171000 | 203224 | 793184
Tasks to be Completed by June 30, 2023
Task 7: [Description]
Sub-task 7.1 [Description] | [6 empty] | 0 | 0
Sub-task 7.2 [Description] | [6 empty] | 0 | 0
Sub-task 7.3 [Description] | [6 empty] | 0 | 0
Total Task 7 Cost |  |  |  | 0 | 0 | 0 | 0 | 0
Task 8: [Description]
Sub-task 8.1 [Description] | [6 empty] | 0 | 0
Sub-task 8.2 [Description] | [6 empty] | 0 | 0
Sub-task 8.3 [Description] | [6 empty] | 0 | 0
Total Task 8 Cost |  |  |  | 0 | 0 | 0 | 0 | 0
Task 9: [Description]
Sub-task 9.1 [Description] | [6 empty] | 0 | 0
Sub-task 9.2 [Description] | [6 empty] | 0 | 0
Sub-task 9.3 [Description] | [6 empty] | 0 | 0
Total Task 9 Cost |  |  |  | 0 | 0 | 0 | 0 | 0
Task 10: [Description]
Sub-task 10.1 [Description] | [6 empty] | 0 | 0
Sub-task 10.2 [Description] | [6 empty] | 0 | 0
Sub-task 10.3 [Description] | [6 empty] | 0 | 0
Total Task 10 Cost |  |  |  | 0 | 0 | 0 | 0 | 0
Task 11: [Description]
Sub-task 11.1 [Description] | [6 empty] | 0 | 0
Sub-task 11.2 [Description] | [6 empty] | 0 | 0
Sub-task 11.3 [Description] | [6 empty] | 0 | 0
Total Task 11 Cost |  |  |  | 0 | 0 | 0 | 0 | 0
Required Task 12: Reporting
Sub-task 12.1 Monthly progress reports FY23 (template provided) | Monthly progress reports submitted by the 30th of each month of the grant period to your MVP Regional Coordinator |  |  | 0 |  |  | 0 | 0
Sub-task 12.2 Project Case Study if project ends in FY23 (template provided) | Final case study report, powerpoint slide, project photos |  |  | 0 |  |  | 0 | 0
Total Task 12 Cost |  |  |  | 0 | 0 | 0 | 0 | 0
TOTAL PROJECT COST FY23 |  |  |  | 0 | 0 | 0 | 0 | 0
TOTAL PROJECT COST OVERALL |  |  |  | 589960 | 32224 | 171000 | 203224 | 793184
[7 empty] | 25.62% | (Note: Match must be at least 25% of total project cost)

## CommBuysOPTIONAL BUDGET WORKSHE
Optional FY22 [/FY23] MVP Action Grant Budget Details Worksheet
| GRANT | [11 empty] | Total Task (Grant) | MATCH
| Project Team Hours | [7 empty] | Direct Costs |  |  |  |  | Project Team Hours | [16 empty] | Direct Costs
| Town Administrator |  | Asst. Town Administrator |  | DPW Director |  | Position/Title |  | Unit | Quanity | Unit Cost | Total |  | Town Administrator |  | Asst. Town Adiminstrator |  | DPW Director |  | Asst. DPW Director |  | Harbormaster |  | Conservation Agent |  | FHR Executive Director |  | FHR Asst Project Manager |  | Total | Unit | Quanity | Unit Cost | Total | Total Task (Match) | Total Project Cost
Hourly Rate | 0 |  | 0 |  | 0 |  | 0 |  | X | X | X | X |  | 76.92 |  | 46.86 |  | 55.43 |  | 46.51 |  | 45.59 |  | 43.43 |  | 56.04 |  | 34.61 |  |  | X | X | X | X
Tasks to be Completed by June 30, 2022
Required Task 0: Project kickoff | Hours | Total | Hours | Total | Hours | Total | Hours | Total | [5 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 0.1: Kick-off meeting with Town, EEA, and Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 153.84 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 86.86 | 2 | 112.08 | 4 | 138.44 | 491.22 |  | 0 | 0 | 0 | 491.22 | 491.22
Total Task 0 Cost | [12 empty] | 0 | [21 empty] | 491.22 | 491.22
Task 1: Chequessett Neck Road Bridge and Water Access Facility Construction Plans and Bid Specifications | Hours | Total | Hours | Total | Hours | Total | Hours | Total | [5 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 1.1 Review/Update 60% Design Documents
Sub-task 1.2 Develop Traffic Management Plan
Sub-task 1.3 Prepare Draft Final Design Plans
Sub-task 1.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1538.4 | 40 | 3076.8 | 1 | 76.92 | 2 | 86.86 | 1 | 56.04 | 20 | 692.2 | 5527.22 |  | 0 | 0 | 0 | 5527.22 | 5527.22
Sub-task 1.5 MassDOT PS&E Final Review and Coordination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 76.92 | 2 | 153.84 | 10 | 769.2 | 20 | 1538.4 | 1 | 76.92 | 0 | 0 | 1 | 56.04 | 10 | 346.1 | 3017.42 |  | 0 | 0 | 0 | 3017.42 | 3017.42
Sub-task 1.6 Town and DOT Review/Coordination Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 153.84 | 6 | 461.52 | 6 | 461.52 | 10 | 769.2 | 2 | 153.84 | 4 | 173.72 | 2 | 112.08 | 20 | 692.2 | 2977.92 |  | 0 | 0 | 0 | 2977.92 | 2977.92
Total Task 1 Cost | [12 empty] | 0 | [21 empty] | 11522.56 | 11522.56
Task 2: High Toss Road Construction Plans and Bid Specifications | [13 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 2.1 Review/Update 60% Design Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 86.86 | 0 | 0 | 2 | 69.22 | 156.08 |  | 0 | 0 | 0 | 156.08 | 156.08
Sub-task 2.2 Develop Traffic Management Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 76.92 | 2 | 153.84 | 2 | 153.84 | 3 | 230.76 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 69.22 | 684.58 |  | 0 | 0 | 0 | 684.58 | 684.58
Sub-task 2.3 Prepare Draft Final Design Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 112.08 | 2 | 69.22 | 181.3 |  | 0 | 0 | 0 | 181.3 | 181.3
Sub-task 2.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 153.84 | 1 | 76.92 | 2 | 153.84 | 0 | 0 | 0 | 0 | 1 | 56.04 | 6 | 207.66 | 648.3 |  | 0 | 0 | 0 | 648.3 | 648.3
Sub-task 2.5 Meetings and Project Communication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 76.92 | 2 | 153.84 | 2 | 153.84 | 4 | 307.68 | 0 | 0 | 1 | 43.43 | 1 | 56.04 | 8 | 276.88 | 1068.63 |  | 0 | 0 | 0 | 1068.63 | 1068.63
Total Task 2 Cost | [12 empty] | 0 | [21 empty] | 2738.89 | 2738.89
Task 3: Low-Lying Roads Elevation and Culvert Replacements Construction Plans and Bid Specifications | [13 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 3.1 Review/Update 60% Design Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 138.44 | 138.44 |  | 0 | 0 | 0 | 138.44 | 138.44
Sub-task 3.2 Develop Traffic Management Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 153.84 | 2 | 153.84 | 8 | 615.36 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 138.44 | 1061.48 |  | 0 | 0 | 0 | 1061.48 | 1061.48
Sub-task 3.3 Prepare Draft Final Design Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 4 | 307.68 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 138.44 | 523.04 |  | 0 | 0 | 0 | 523.04 | 523.04
Sub-task 3.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 1 | 76.92 | 2 | 153.84 | 0 | 0 | 0 | 0 | 1 | 56.04 | 10 | 346.1 | 709.82 |  | 0 | 0 | 0 | 709.82 | 709.82
Sub-task 3.5 Meetings and Project Communication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 76.92 | 2 | 153.84 | 1 | 76.92 | 4 | 307.68 | 0 | 0 | 1 | 43.43 | 1 | 56.04 | 8 | 276.88 | 991.71 |  | 0 | 0 | 0 | 991.71 | 991.71
Total Task 3 Cost | [12 empty] | 0 | [21 empty] | 3424.49 | 3424.49
Task 4: Low-Lying Property Mitigation, Way #672 (25 and 27 Way #672) Construction Plans and Bid Specifications | [13 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 4.1 Review/Update 60% Design Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 112.08 | 8 | 276.88 | 465.88 |  | 0 | 0 | 0 | 465.88 | 465.88
Sub-task 4.2 Develop Traffic Management Plan | [25 empty] | 1 | 56.04 | 6 | 207.66 | 263.7 |  |  |  | 0 | 263.7 | 263.7
Sub-task 4.3 Prepare Draft Final Design Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 56.04 | 10 | 346.1 | 479.06 |  | 0 | 0 | 0 | 479.06 | 479.06
Sub-task 4.4 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 1 | 76.92 | 0 | 0 | 0 | 0 | 1 | 56.04 | 10 | 346.1 | 555.98 |  | 0 | 0 | 0 | 555.98 | 555.98
Sub-task 4.5 Meetings and Project Communication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 153.84 | 3 | 230.76 | 3 | 230.76 | 6 | 461.52 | 0 | 0 | 0 | 0 | 3 | 168.12 | 10 | 346.1 | 1591.1 |  | 0 | 0 | 0 | 1591.1 | 1591.1
Total Task 4 Cost | [12 empty] | 0 | [21 empty] | 3355.72 | 3355.72
Task 5: Low-Lying Property Mitigation, Miller-Frederiksen (695 Bound Brook Island Road) Construction Plans and Bid Specifications | [13 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 5.1 Review/Update 60% Design Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 69.22 | 69.22 |  | 0 | 0 | 0 | 69.22 | 69.22
Sub-task 5.2 Prepare Draft Final Design Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 69.22 | 69.22 |  | 0 | 0 | 0 | 69.22 | 69.22
Sub-task 5.3 Update/Finalize Design Plans, Details, Specifications, Bid Documents and Cost Estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 0 | 0 | 1 | 76.92 | 0 | 0 | 0 | 0 | 1 | 56.04 | 4 | 138.44 | 348.32 |  | 0 | 0 | 0 | 348.32 | 348.32
Sub-task 5.4 Meetings and Project Communication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 76.92 | 2 | 153.84 | 1 | 76.92 | 2 | 153.84 | 0 | 0 | 2 | 86.86 | 1 | 56.04 | 4 | 138.44 | 742.86 |  | 0 | 0 | 0 | 742.86 | 742.86
Total Task 5 Cost | [12 empty] | 0 | [21 empty] | 1229.62 | 1229.62
Task 6: Chequessett Yacht and Country Club Reconfiguration Construction Plans and Bid Specifications | [13 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 6.1 Review/Update 60% Deisign Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 307.68 | 0 | 0 | 0 | 0 | 2 | 69.22 | 376.9 |  | 0 | 0 | 0 | 376.9 | 376.9
Sub-task 6.2 Draft and Final Construction Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 0 | 0 | 0 | 0 | 2 | 69.22 | 146.14 |  | 0 | 0 | 0 | 146.14 | 146.14
Sub-task 6.3 Draft and Final Bid Specifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76.92 | 2 | 153.84 | 0 | 0 | 1 | 56.04 | 8 | 276.88 | 563.68 |  | 0 | 0 | 0 | 563.68 | 563.68
Sub-task 6.4 Meetings and Communcation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 76.92 | 2 | 153.84 | 1 | 76.92 | 2 | 153.84 | 0 | 0 | 0 | 0 | 1 | 56.04 | 4 | 138.44 | 656 |  | 0 | 0 | 0 | 656 | 656
Total Task 6 Cost | [12 empty] | 0 | [21 empty] | 1742.72 | 1742.72
Task 7: Public Involvement and Community Engagement Plan | [13 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Outreach Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1120.8 | 10 | 346.1 | 1466.9 |  | 1 | 5000 | 5000 | 6466.9 | 6466.9
Public meetings (HREC, HRSG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 8 | 615.36 | 4 | 307.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 560.4 | 0 | 0 | 1483.44 |  | 0 | 0 | 0 | 1483.44 | 1483.44
Special Events; personnal meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2241.6 | 0 | 0 | 2241.6 |  | 0 | 0 | 0 | 2241.6 | 2241.6
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total Task 7 Cost | [12 empty] | 0 | [21 empty] | 10191.94 | 10191.94
Required Task 8: Reporting | [13 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 8.1 Monthly progress reports FY22 (template provided) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 461.52 | 0 | 0 | 1 | 76.92 | 0 | 0 | 2 | 86.86 | 6 | 336.24 | 20 | 692.2 | 1653.74 |  | 0 | 0 | 0 | 1653.74 | 1653.74
Sub-task 8.2 Project Case Study (template provided) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 153.84 | 0 | 0 | 0.5 | 38.46 | 0 | 0 | 2 | 86.86 | 3 | 168.12 | 10 | 346.1 | 793.38 |  | 0 | 0 | 0 | 793.38 | 793.38
Total Task 8 Cost | [12 empty] | 0 | [21 empty] | 2447.12 | 2447.12
TOTAL PROJECT COST FY22 | [12 empty] | 0 | [21 empty] | 37144.28 | 37144.28
Tasks to be Completed by June 30, 2023
Task 7: | Hours | Total | Hours | Total | Hours | Total | Hours | Total | [5 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total Task 7 Cost | [12 empty] | 0 | [21 empty] | 0 | 0
Task 8:
Sub-task 8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total Task 8 Cost | [12 empty] | 0 | [21 empty] | 0 | 0
Task 9:
Sub-task 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total Task 9 Cost | [12 empty] | 0 | [21 empty] | 0 | 0
Task 10:
Sub-task 10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total Task 10 Cost | [12 empty] | 0 | [21 empty] | 0 | 0
Task 11:
Sub-task 11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total Task 11 Cost | [12 empty] | 0 | [21 empty] | 0 | 0
Task 12:
Sub-task 12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sub-task 12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total Task 12 Cost | [12 empty] | 0 | [21 empty] | 0 | 0
TOTAL PROJECT COST FY23 | [12 empty] | 0 | [21 empty] | 0 | 0
TOTAL PROJECT COST OVERALL | [12 empty] | 0 | [21 empty] | 37144.28 | 37144.28
[35 empty] | 100% | (Note: Match must be at least 25% of total project cost)